## Slide 1: Educational Master Plan (EMP) Summer Timeline (Phase II)
July 29, 2015
E. Kuo
FH IR&P

## Slide 2
Phase I Completed:
January-June 2015
Environmental Scan
Focus Groups and Interviews
Institutional Goals
Internal (student) data
External (community) data
Preliminary draft goals for the next 5-8 years
Documented campus and community voices

## Slide 3
Phase II: July-September 2015
Align the EMP goals with college mission
Identify strategic plans based on the EMP goals
Finalize outline and sections of the EMP
Determine content of the EMP Opening Day presentation
Identify short-term and long-term plans with examples
Review each proposed goal, referencing the college mission (and vision)
Identify what should be communicated with college community (feedback opportunity)
Confirm topics to be included in the EMP

## Slide 4
Phase II Meeting Dates and Times
8/20/15 11-12:30
Align EMP with college missions
9/02/15 11-12:30
Review EMP draft and organization
9/09/15 1:30-3
Feedback on EMP draft
Develop strategic action plans
Continue with developing strategic action plans
Add strategic action plan section to EMP draft
EMP Opening Day presentation

## Slide 5
Phase III:
September-December 2015
Opening Day
Presentation
Workshop
Working Draft
College planning
Governance process
EMP Steering Committee
Strategic action plans
Feedback and contribution to the EMP draft
EMP Process
Environmental Scan
Ed Center
Online Ed
EMP Goals
Institutional standards and goals
EMP to Board of Trustees for approval
12/07/15

## Slide 6
http://foothill.edu/president/parc/esmp.php
For More Information: